## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Jacob Ndayishimiye | Team lead: repo security, branch protection, board, documentation | j.ndayishim@alustudent.com
Joshua Ochel Mugisha | Backend: quiz API and scoring (issues #4-#6) | o.mugisha2@alustudent.com
Ewing Keylan | USSD menu and unit tests (issues #7-#9) | e.singasara@alustudent.com
Olaniyi Olufemi | DevOps: Docker, GitHub Actions CI, Terraform (issues #10-#12) | o.olufemi@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Secure repo setup: .gitignore, LICENSE, CODEOWNERS, PR/issue templates (#1) | Jacob Ndayishimiye | 2026-10-21 | Completed | Yes | Pushed to main; awaiting team review
| Enable branch protection on main (#2) | Jacob Ndayishimiye | 2026-10-22 | Completed | Yes | Rules documented in docs/BRANCH_PROTECTION.md; applying after CI exists
| README with project description and setup (#3) | Jacob Ndayishimiye | 2026-10-22 | Completed | Yes | Setup section to be verified once the API is merged
| Quiz API: subjects, quiz, submit/score endpoints (#4-#6) | Joshua Ochel Mugisha | 2026-10-23 | Completed | Yes | Branch: feature/quiz-api-joshua
| USSD-style menu, 2+ levels (#7) | Ewing Keylan | 2026-10-22 | Completed | Yes | Branch: feature/ussd-menu-ewing
| Unit tests with pytest (#8) | Ewing Keylan | 2026-10-23 | Completed | Yes | Depends on #4-#7
| Dockerfile and docker-compose (#10) | Olaniyi Olufemi | 2026-10-23 | Completed | Yes | Branch: devops/docker-olaniyi
| GitHub Actions CI: lint, test, docker-build (#11) | Olaniyi Olufemi | 2026-10-23 | Completed | Yes | Job names are the required status checks
| Terraform skeleton (#12) | Olaniyi Olufemi | 2026-10-23 | Completed | Yes | Formative 2 milestone
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-10-20 | Define the SomaQuiz problem and decide the first usable features | Jacob Ndayishimiye | Jacob, Joshua, Ewing, Olaniyi | The team agreed to build a lightweight exam-practice platform for students who may use low-end phones or have limited internet access. The first features were identified as subject selection, quiz generation, scoring, and a USSD-style menu. | Finalise the project description and divide the development tasks among team members.
2026-10-21 | Organise the repository and assign development responsibilities | Jacob Ndayishimiye | Jacob, Joshua, Ewing, Olaniyi | The team reviewed the repository structure and assigned backend work to Joshua, USSD and testing work to Ewing, DevOps work to Olaniyi, and security/documentation work to Jacob. | Create the relevant GitHub issues, assign team members, and begin work on separate branches.
2026-10-23 | Coordinate the quiz API and USSD service boundaries | Jacob Ndayishimiye | Jacob, Joshua, Ewing, Olaniyi | Joshua worked on the subject, quiz, and scoring endpoints. Ewing discussed how the USSD menu would use subject and question selections. The team agreed that the USSD menu should first be developed as a standalone module before later API integration. | Complete the quiz API implementation and build the first two-level USSD menu.
2026-10-23 | Review containerisation, CI checks, and Terraform preparation | Jacob Ndayishimiye | Jacob, Joshua, Ewing, Olaniyi | The team reviewed the Docker setup, GitHub Actions jobs, test execution, and Terraform folder structure. The required CI checks were identified as linting, tests, and Docker image building. | Resolve review comments and verify that the CI workflow can run against the current project structure.
2026-10-23 | Review pull requests and prepare evidence for the formative submission | Jacob Ndayishimiye | Jacob, Joshua, Ewing, Olaniyi | The team reviewed the backend, DevOps, and USSD branches. They discussed pull-request approvals, protected main, meaningful commits, completed board cards, and the information required in the participation sheet. | Finish outstanding reviews, merge approved work, update task statuses, and complete the final submission records.